## Feature Audit
System / Module | Category | Feature / Functionality | Description / What It Should Do | Priority | Exists in My Application? | Implementation Status | Pending Implementations | Notes / Current Behavior
Retail POS | POS & Billing | New Sale / POS Checkout | Create a customer sale from a POS screen. | Critical | Yes | Implemented
Retail POS | POS & Billing | Barcode Scanning | Scan product barcodes to add products to a sale. | High | Yes | Implemented
Retail POS | POS & Billing | Product Search | Search products by name, SKU, barcode or category. | Critical | Yes | Implemented
Retail POS | POS & Billing | Quick Sale | Sell an item/service without a full product setup. | Medium | Yes | Implemented
Retail POS | POS & Billing | Hold / Resume Sale | Temporarily hold a transaction and resume it later. | Medium | No | Not Started | Pending: Multi-cart parking and resuming saved carts.
Retail POS | POS & Billing | Receipt Generation | Generate and print/email customer receipts. | High | Yes | Implemented
Retail POS | POS & Billing | Sales Return | Process complete or partial sales returns. | Critical | Yes | Implemented
Retail POS | POS & Billing | Exchange | Exchange sold products for other products. | Medium | No | Not Started | Pending: Direct item-for-item exchange with price difference settlement.
Retail POS | Payments | Cash Payment | Accept and record cash payments. | Critical | Yes | Implemented
Retail POS | Payments | Card Payment | Accept and record card payments. | Critical | Yes | Implemented
Retail POS | Payments | Zelle / Bank Payment | Record supported electronic/manual payment methods. | High | Yes | Implemented
Retail POS | Payments | Split Payment | Allow one transaction to be paid using multiple payment methods. | High | Yes | Implemented
Retail POS | Payments | Refund | Issue full or partial refunds. | Critical | Yes | Implemented
Retail POS | Cash Management | Cash Drawer Opening | Record opening cash balance for a cashier/shift. | High | No | Not Started | Pending: Opening till/register cash balance entry at start of shift.
Retail POS | Cash Management | Cash In / Cash Out | Record non-sale cash movements. | High | No | Not Started | Pending: Logging non-sale petty cash additions and withdrawals.
Retail POS | Cash Management | Shift Closing / Reconciliation | Compare expected and actual cash at shift close. | Critical | No | Not Started | Pending: Cashier shift closing and expected vs actual cash count report.
Retail POS | Products | Product Master | Create and maintain product information. | Critical | Yes | Implemented
Retail POS | Products | Categories | Organize products into categories. | High | Yes | Implemented
Retail POS | Products | Brands | Manage product brands/manufacturers. | Medium | Partial | Partially Implemented | Stored as a text attribute on products; Pending: Dedicated Brand Master table.
Retail POS | Products | SKU Management | Create/manage unique product SKUs. | Critical | Yes | Implemented
Retail POS | Products | Barcode Management | Assign/manage product barcodes. | High | Yes | Implemented
Retail POS | Products | Product Variants | Manage size, color, pack, pot size or other variants. | High | Partial | Partially Implemented | Product schema supports size/color/pot size; variant selector in UI.
Retail POS | Pricing | Retail Pricing | Configure selling prices. | Critical | Yes | Implemented
Retail POS | Pricing | Discounts | Apply fixed or percentage discounts. | High | Yes | Implemented
Retail POS | Pricing | Coupons | Create and validate coupon codes. | Medium | Yes | Implemented
Retail POS | Pricing | Customer-specific Pricing | Support special pricing for customers/groups. | Medium | No | Not Started
Retail POS | Tax | Tax Configuration | Configure applicable tax rates/rules. | Critical | Yes | Implemented
Retail POS | Customers | Customer Profiles | Maintain customer contact and account information. | High | Yes | Implemented
Retail POS | Customers | Purchase History | View customer transaction history. | High | Yes | Implemented
Retail POS | Customers | Customer Credit / Balance | Track outstanding customer balances. | High | Yes | Implemented
Retail POS | Inventory | Stock Quantity | Track available product quantities. | Critical | Yes | Implemented
Retail POS | Inventory | Stock Adjustment | Manually increase/decrease stock with a reason. | Critical | Yes | Implemented
Retail POS | Inventory | Stock Transfer | Transfer stock between stores/warehouses. | High | Partial | Partially Implemented | Warehouse locations exist; Pending: Inter-store transfer dispatch/receive flow.
Retail POS | Inventory | Damaged / Lost Stock | Record inventory losses and damaged products. | High | Partial | Partially Implemented | Logged as stock adjustments; Pending: Dedicated damaged stock report.
Retail POS | Purchasing | Vendor Management | Create and maintain vendor/supplier records. | High | Yes | Implemented
Retail POS | Purchasing | Purchase Order | Create purchase orders for suppliers. | High | Yes | Implemented
Retail POS | Purchasing | Goods Receiving | Receive products against purchases. | Critical | Yes | Implemented
Retail POS | Purchasing | Purchase Invoice | Record supplier invoices and costs. | High | Yes | Implemented
Retail POS | Employees | Employee Management | Manage employees and staff accounts. | High | Yes | Implemented
Retail POS | Employees | Roles & Permissions | Control access to POS features by role. | Critical | Yes | Implemented
Retail POS | Stores | Multi-store Management | Manage multiple retail locations. | Medium | Partial | Partially Implemented | Tenant structure and pickup locations exist; Pending: Separate store registers.
Retail POS | Stores | Store-level Inventory | Track inventory separately by location. | High | No | Not Started | Pending: Independent stock levels per retail branch.
Retail POS | Hardware | Barcode Scanner Integration | Connect and use barcode scanner hardware. | High | Yes | Implemented
Retail POS | Hardware | Receipt Printer Integration | Print receipts through POS hardware. | Medium | Yes | Implemented
Retail POS | Hardware | Cash Drawer Integration | Open/control cash drawer from POS. | Medium | Partial | Partially Implemented | Opens via printer kick-out pulse; Pending: Direct OPOS USB kick drawer.
Retail POS | Reports | Sales Report | Analyze sales by date, store, employee and product. | Critical | Yes | Implemented
Retail POS | Reports | Profit Report | Analyze revenue, cost and profit. | Critical | Yes | Implemented
Retail POS | Reports | Tax Report | Summarize taxable sales and tax collected. | High | Yes | Implemented
Retail POS | Reports | Inventory Report | Analyze stock quantities and inventory value. | High | Yes | Implemented
Retail POS | Reports | Payment Report | Analyze payments by method. | High | Yes | Implemented
Retail POS | Analytics | Top Products | Identify best-selling products. | Medium | Yes | Implemented
Retail POS | Analytics | Slow-moving Products | Identify products with low sales velocity. | Medium | Partial | Partially Implemented | Basic product sales volume available; Pending: Dedicated aging velocity report.
Retail POS | Analytics | Sales Trends | View sales performance over time. | Medium | Yes | Implemented
Landscaping / Service Management | Customers | Customer Management | Manage landscaping customers and contact information. | Critical | Yes | Implemented
Landscaping / Service Management | Property | Property Management | Store property/address information for each customer. | Critical | Yes | Implemented
Landscaping / Service Management | Property | Property Measurements | Capture dimensions/measurements needed for estimating. | Critical | Yes | Implemented
Landscaping / Service Management | Service Catalog | Service Management | Create and manage landscaping services. | Critical | Yes | Implemented
Landscaping / Service Management | Service Catalog | Service Packages | Bundle multiple landscaping services into packages. | Medium | Partial | Partially Implemented | Line items can be combined in quotes; Pending: Standalone package bundles.
Landscaping / Service Management | Estimating | Estimate Creation | Create estimates from customer/property/service information. | Critical | Yes | Implemented
Landscaping / Service Management | Estimating | Material Calculation | Calculate material quantities and material cost. | Critical | Yes | Implemented
Landscaping / Service Management | Estimating | Labor Calculation | Calculate labor hours and labor cost. | Critical | Yes | Implemented
Landscaping / Service Management | Estimating | Equipment Calculation | Calculate equipment hours and equipment cost. | High | Yes | Implemented
Landscaping / Service Management | Estimating | Disposal / Hauling Calculation | Calculate disposal, hauling, dump fees and related costs. | High | Partial | Partially Implemented | Entered as miscellaneous line items; Pending: Automated dump fee formula.
Landscaping / Service Management | Estimating | Miscellaneous Cost | Add configurable miscellaneous costs to an estimate. | High | Yes | Implemented
Landscaping / Service Management | Estimating | Overhead Calculation | Allocate overhead using fixed or percentage methods. | Critical | Partial | Partially Implemented | Handled via markup %; Pending: Fixed company overhead % allocator.
Landscaping / Service Management | Estimating | Profit / Margin Calculation | Calculate markup, profit or gross-margin based selling price. | Critical | Yes | Implemented
Landscaping / Service Management | Estimating | Engineering Cost | Add engineering/design/structural engineering costs. | High | No | Not Started
Landscaping / Service Management | Estimating | Permit Cost | Add permit fees/costs to estimates. | High | No | Not Started
Landscaping / Service Management | Estimating | Waste Factor | Apply configurable waste factors to materials. | High | No | Not Started
Landscaping / Service Management | Estimating | Unit Conversion | Convert ft, sq ft, yd, cu yd, ton, etc. for estimating. | High | Partial | Partially Implemented | Units supported (ft, sq ft, yd); Pending: In-line dynamic unit converter.
Landscaping / Service Management | Structural Check | Engineering Required? | Determine whether engineering is required based on project rules. | Critical | No | Not Started
Landscaping / Service Management | Structural Check | Permit Required? | Determine whether permit is required based on project rules/location. | Critical | No | Not Started
Landscaping / Service Management | Structural Check | Geogrid Required? | Determine whether geogrid/reinforcement is required. | High | No | Not Started
Landscaping / Service Management | Structural Check | Footing Required? | Determine whether a footing/base system is required. | High | No | Not Started
Landscaping / Service Management | Structural Check | Tie-back Required? | Determine whether tie-backs/anchors are required. | High | No | Not Started
Landscaping / Service Management | Structural Check | Site Conditions | Capture slope, soil, drainage, access, rock, water and existing wall conditions. | Critical | No | Not Started
Landscaping / Service Management | Quotes | Quote Creation | Convert estimate into a customer-facing quote. | Critical | Yes | Implemented
Landscaping / Service Management | Quotes | Quote Versioning | Maintain versions/revisions of quotes. | Medium | Yes | Implemented
Landscaping / Service Management | Quotes | Quote Approval | Track accepted/rejected/pending quote status. | Critical | Yes | Implemented
Landscaping / Service Management | Quotes | Quote PDF | Generate downloadable/printable quote documents. | High | Yes | Implemented
Landscaping / Service Management | Scheduling | Job Scheduling | Schedule service jobs by date/time. | Critical | Yes | Implemented
Landscaping / Service Management | Scheduling | Calendar | Calendar view of upcoming jobs and appointments. | High | Yes | Implemented
Landscaping / Service Management | Scheduling | Crew Assignment | Assign employees/crews to jobs. | Critical | Yes | Implemented
Landscaping / Service Management | Jobs | Job Creation | Create a job from an approved quote/service order. | Critical | Yes | Implemented
Landscaping / Service Management | Jobs | Job Status | Track planned, scheduled, in-progress and completed status. | Critical | Yes | Implemented
Landscaping / Service Management | Jobs | Job Notes | Store job/site notes and instructions. | High | Yes | Implemented
Landscaping / Service Management | Jobs | Before / After Photos | Capture job photos for documentation. | Medium | Yes | Implemented
Landscaping / Service Management | Crew | Crew Management | Manage landscaping workers/teams. | High | Yes | Implemented
Landscaping / Service Management | Crew | Labor Tracking | Track actual labor hours against estimates. | High | Partial | Partially Implemented | logs hours; Pending: Automated estimated vs actual variance report
Landscaping / Service Management | Equipment | Equipment Management | Manage equipment used on landscaping jobs. | High | Yes | Implemented
Landscaping / Service Management | Equipment | Equipment Rates | Configure hourly/daily equipment rates. | High | Yes | Implemented
Landscaping / Service Management | Materials | Material Catalog | Maintain landscaping materials and unit costs. | Critical | Yes | Implemented
Landscaping / Service Management | Materials | Material Usage | Track material consumed on a job. | High | Partial | Partially Implemented | Billed on jobs; Pending: Post-job warehouse consumption reconciliation.
Landscaping / Service Management | Invoicing | Service Invoice | Create invoices for completed/approved services. | Critical | Yes | Implemented
Landscaping / Service Management | Invoicing | Deposit / Progress Billing | Support deposits and milestone/progress billing. | High | Yes | Implemented
Landscaping / Service Management | Invoicing | Outstanding Balance | Track customer balances and due amounts. | Critical | Yes | Implemented
Landscaping / Service Management | Payments | Service Payments | Record payments against landscaping invoices. | Critical | Yes | Implemented
Landscaping / Service Management | Reports | Job Profitability | Compare estimated versus actual revenue/cost/profit. | Critical | Partial | Partially Implemented | Quote margins calculated; Pending: Post-job actual cost vs revenue sheet.
Landscaping / Service Management | Reports | Estimate vs Actual | Compare estimated materials/labor/equipment with actuals. | High | Partial | Partially Implemented | Data stored in timesheets/invoices; Pending: Dedicated comparison report.
Landscaping / Service Management | Reports | Crew Performance | Analyze crew hours, jobs and productivity. | Medium | Partial | Partially Implemented | Hours logged per worker; Pending: Crew productivity analytics.
E-commerce | Storefront | Home Page | Customer-facing e-commerce home page. | Critical | Yes | Implemented
E-commerce | Storefront | Category Browsing | Browse products by category. | Critical | Yes | Implemented
E-commerce | Storefront | Product Search | Search products by keywords and attributes. | Critical | Yes | Implemented
E-commerce | Storefront | Product Filters | Filter products by price, brand, category, attributes, etc. | High | Yes | Implemented
E-commerce | Storefront | Product Details | Display images, description, pricing, stock and details. | Critical | Yes | Implemented
E-commerce | Storefront | Related Products | Show related/cross-sell products. | Medium | Partial | Partially Implemented | Category-based items shown; Pending: Smart recommendation algorithm.
E-commerce | Storefront | Product Recommendations | Recommend products based on business rules or behavior. | Medium | No | Not Started
E-commerce | Shopping | Shopping Cart | Add, remove and update products in cart. | Critical | Yes | Implemented
E-commerce | Shopping | Wishlist | Save products for later. | Medium | Partial | Partially Implemented | Pending: Customer storefront wishlist page.
E-commerce | Shopping | Coupon Application | Apply and validate coupon codes in cart/checkout. | High | Yes | Implemented
E-commerce | Checkout | Customer Checkout | Complete checkout for an order. | Critical | Yes | Implemented
E-commerce | Checkout | Address Management | Create/manage billing and shipping addresses. | Critical | Yes | Implemented
E-commerce | Checkout | Tax Calculation | Calculate applicable tax for online orders. | Critical | Yes | Implemented
E-commerce | Checkout | Shipping Calculation | Calculate shipping charges. | Critical | Yes | Implemented
E-commerce | Checkout | Payment Gateway | Process online payments through payment gateway. | Critical | Yes | Implemented
E-commerce | Checkout | Guest Checkout | Allow checkout without account creation. | Medium | Yes | Implemented
E-commerce | Orders | Order Creation | Create customer orders from checkout. | Critical | Yes | Implemented
E-commerce | Orders | Order Status Tracking | Track pending, confirmed, processing, shipped, delivered, etc. | Critical | Yes | Implemented
E-commerce | Orders | Order Cancellation | Allow/administer order cancellation. | High | Yes | Implemented
E-commerce | Orders | Returns | Manage online product returns. | High | Partial | Partially Implemented | Pending: Full customer RMA self-service portal.
E-commerce | Orders | Refunds | Process full or partial order refunds. | Critical | Yes | Implemented
E-commerce | Inventory | Real-time Stock Availability | Show available inventory to customers. | Critical | Yes | Implemented
E-commerce | Inventory | Reserved Stock | Reserve inventory for pending/confirmed orders. | High | Partial | Partially Implemented | Stock deducted on order completion; Pending: Temporary cart lock timer.
E-commerce | Inventory | Out-of-stock Handling | Prevent/flag purchases when inventory is unavailable. | Critical | Yes | Implemented
E-commerce | Warehouse | Pick List | Generate items that warehouse staff need to pick. | High | No | Not Started
E-commerce | Warehouse | Packing | Track packing of orders. | High | No | Not Started
E-commerce | Warehouse | Shipment Creation | Create shipment information for orders. | High | Yes | Implemented
E-commerce | Shipping | Shipping Zones | Define delivery areas/zones. | High | Partial | Partially Implemented | Radius and distance zones configured; Pending: Geofenced polygon maps.
E-commerce | Shipping | Shipping Rules | Configure free/fixed/conditional shipping rules. | High | Yes | Implemented
E-commerce | Shipping | Carrier Integration | Integrate with shipping carrier APIs. | High | No | Not Started
E-commerce | Shipping | Shipping Label | Generate shipping labels. | High | No | Not Started
E-commerce | Shipping | Tracking Number | Store/display shipment tracking information. | High | Yes | Implemented
E-commerce | Shipping | Carrier Webhooks | Receive shipment status updates automatically. | Medium | No | Not Started
E-commerce | Customer | Customer Account | Customer login/profile/account management. | Critical | Yes | Implemented
E-commerce | Customer | Order History | Show customer order history. | High | Yes | Implemented
E-commerce | Customer | Saved Addresses | Save multiple customer addresses. | Medium | Yes | Implemented
E-commerce | Marketing | Promotions | Create product/store promotions. | High | Partial | Partially Implemented | coupon discounts exist; Pending: Marketing campaign scheduler.
E-commerce | Marketing | Discount Rules | Configure conditional discounts. | High | Yes | Implemented
E-commerce | Marketing | Abandoned Cart | Track and recover abandoned shopping carts. | Medium | No | Not Started
E-commerce | Reviews | Product Reviews | Allow customers to review/rate products. | Medium | No | Not Started
E-commerce | Notifications | Order Notifications | Send order confirmation/status notifications. | High | Yes | Implemented
E-commerce | Notifications | Shipping Notifications | Notify customers of shipping/delivery updates. | High | Yes | Implemented
E-commerce | Analytics | E-commerce Sales | Analyze online sales and revenue. | High | Yes | Implemented
E-commerce | Analytics | Conversion Rate | Track visits-to-order conversion. | Medium | No | Not Started
E-commerce | Analytics | Cart Abandonment | Analyze abandoned carts. | Medium | No | Not Started
Shared Platform / Core | Company | Company Profile | Company name, logo, address and business settings. | Critical | Yes | Implemented
Shared Platform / Core | Company | Business Locations | Manage stores, offices, warehouses and service locations. | High | Partial | Partially Implemented | Pickup locations and warehouse zones supported; Pending: Multi-branch hierarchy.
Shared Platform / Core | Configuration | Currency | Configure supported business currency. | Critical | Yes | Implemented
Shared Platform / Core | Configuration | Timezone | Configure timezone for transactions and reports. | Critical | Yes | Implemented
Shared Platform / Core | Configuration | Business Hours | Configure operating/service hours. | Medium | Partial | Partially Implemented | Stored in company config; Pending: Automated slot restriction logic.
Shared Platform / Core | Users | User Management | Create, edit, deactivate and manage users. | Critical | Yes | Implemented
Shared Platform / Core | Users | Roles & Permissions | Role-based access control for modules/actions. | Critical | Yes | Implemented
Shared Platform / Core | Users | Audit Log | Track important user actions and changes. | Critical | Yes | Implemented
Shared Platform / Core | Customers | Unified Customer Profile | Single customer record shared across POS, landscaping and e-commerce. | Critical | Yes | Implemented
Shared Platform / Core | Customers | Customer Activity Timeline | View customer orders, quotes, jobs, invoices and payments in one timeline. | High | Yes | Implemented
Shared Platform / Core | Inventory | Unified Inventory | Shared inventory across POS, e-commerce and service operations. | Critical | Yes | Implemented
Shared Platform / Core | Inventory | Warehouses | Manage multiple warehouses/storage locations. | High | Yes | Implemented
Shared Platform / Core | Inventory | Stock Ledger | Maintain transaction history for inventory movements. | Critical | Yes | Implemented
Shared Platform / Core | Inventory | Low Stock Alerts | Notify users when stock falls below thresholds. | High | Yes | Implemented
Shared Platform / Core | Inventory | Inventory Valuation | Calculate inventory value. | High | Yes | Implemented
Shared Platform / Core | Purchasing | Supplier/Vendor Management | Shared vendor records across product and material purchasing. | High | Yes | Implemented
Shared Platform / Core | Purchasing | Purchase Orders | Centralized purchase order management. | High | Yes | Implemented
Shared Platform / Core | Purchasing | Receiving | Centralized receiving of purchased goods/materials. | Critical | Yes | Implemented
Shared Platform / Core | Finance | Invoices | Centralized invoice management. | Critical | Yes | Implemented
Shared Platform / Core | Finance | Payments | Centralized payment recording and allocation. | Critical | Yes | Implemented
Shared Platform / Core | Finance | Refunds | Centralized refund handling. | High | Yes | Implemented
Shared Platform / Core | Finance | Tax | Central tax configuration/reporting. | Critical | Yes | Implemented
Shared Platform / Core | Finance | Expenses | Record and categorize business expenses. | High | Yes | Implemented
Shared Platform / Core | Notifications | Email Notifications | Send system/customer emails. | High | Yes | Implemented
Shared Platform / Core | Notifications | SMS Notifications | Send SMS alerts where configured. | Medium | Yes | Implemented
Shared Platform / Core | Notifications | In-app Notifications | Show notifications within application. | Medium | Yes | Implemented
Shared Platform / Core | Documents | PDF Generation | Generate invoices, quotes, receipts and reports as PDFs. | High | Yes | Implemented
Shared Platform / Core | Reports | Dashboard | Unified business dashboard with key metrics. | Critical | Yes | Implemented
Shared Platform / Core | Reports | Revenue Report | Revenue across POS, e-commerce and services. | Critical | Yes | Implemented
Shared Platform / Core | Reports | Gross Profit Report | Revenue minus direct costs. | Critical | Yes | Implemented
Shared Platform / Core | Reports | Net Profit Report | Profit after operating expenses/overhead. | High | Yes | Implemented
Shared Platform / Core | Reports | Outstanding Receivables | Track unpaid customer balances. | High | Yes | Implemented
Shared Platform / Core | Reports | Vendor Payables | Track outstanding supplier balances. | High | Yes | Implemented
Shared Platform / Core | Security | Authentication | Secure login/authentication system. | Critical | Yes | Implemented
Shared Platform / Core | Security | Password Reset | Secure password reset/recovery. | Critical | Yes | Implemented
Shared Platform / Core | Security | Session Management | Control active sessions and logout. | High | Yes | Implemented
Shared Platform / Core | Security | Data Backup | Back up important business data. | Critical | No | Not Started
Shared Platform / Core | Integrations | Payment Gateway Integration | Connect external payment provider(s). | Critical | Yes | Implemented
Shared Platform / Core | Integrations | Shipping API Integration | Connect shipping providers. | High | No | Not Started
Shared Platform / Core | Integrations | Accounting Integration | Sync financial data with accounting software. | Medium | No | Not Started
Shared Platform / Core | Integrations | Email Service Integration | Connect transactional email provider. | High | Yes | Implemented
Shared Platform / Core | Integrations | Webhook Support | Send/receive system events with external applications. | Medium | Yes | Implemented

## Audit Summary
Application Feature Audit
How to use this workbook
1. Go to the 'Feature Audit' sheet.
2. For every feature, select whether it exists in your application.
3. Use 'Partial' if the feature exists but is incomplete or works differently.
4. Select the implementation status.
5. Add your current behavior and missing requirements in the Notes columns.
6. Return this updated Excel later and the gaps can be reviewed systematically.
Coverage Summary
Metric | Count | Percentage | Meaning
Total Features | 187 | 100% | Total checklist items
Implemented / Yes | 134 | 71.66% | Features marked as available
Partial | 24 | 12.83% | Features partially available
Missing / No | 29 | 15.51% | Features currently missing
Not Sure | 0 | 0% | Needs verification
Not Yet Checked | 2 | 1.07% | Still needs review
System Coverage
System | Total Features | Yes / Implemented | No / Missing
Retail POS | 53 | 39 | 7
Landscaping / Service Management | 47 | 29 | 9
E-commerce | 45 | 29 | 10
Shared Platform / Core | 42 | 37 | 3

## Dropdown Lists
Exists Options | Implementation Status | Priority
Yes | Implemented | Critical
No | Partially Implemented | High
Partial | Planned | Medium
Not Sure | Not Started | Low
Not Applicable